|  | Implementation of Nigeria Climate Change Response Programme (NCCRP) Contract N°: ENV/2019/409-995 |  |
| --- | --- | --- |

Terms of Reference (ToR)

JUNIOR SHORT-TERM EXPERT (STE)

Provision of Technical Support (Designs) To Produce NCCRP Communications & Visibility Materials

| Reference No. of the Mission | S334/STE/2020/ToR/02-7 |  |
| --- | --- | --- |
| Date of Transmission |  |  |
| Category of Expert | National Non-Key Expert |  |
| Key Experts Responsible | Mr Todd NGARA, Team Leader Mr Kayode EGBELEYE, Capacity Building & Communications Expert |  |
| Title of the Mission | Provision of Technical Support (Designs) To Produce NCCRP Communications & Visibility Materials. |  |
| No. of Working Days (WD) | 70 Working Days |  |
| Indicative Dates | 10/2023 | 05/2024 |
| Duty Station | Abuja (FCT) |  |
| Mission outside of Duty Station | N/A |  |

| Title of the Mission |  |
| --- | --- |
| Name of Project | Implementation of Nigeria Climate Change Response Programme (NCCRP), EuropeAid/140100/DH/SER/NG |
| Contract No. | ENV/2019/409-995 |
| Reference No. of the Mission | S334/STE/2020/ToR/02-7 |
| Context and Justification | Following the ratification of the Paris Agreement in 2017, Nigeria committed itself to reduce its Greenhouse Gas (GHGs) emissions unconditionally by 20% and conditionally by 45% by 2030 in line with its Nationally Determined Contributions (NDC) pledge. To support Nigeria’s efforts towards the fulfilment of its conditional NDC target, the Federal Government of Nigeria is being supported by the European Union (EUD) through the provision of technical assistance for the implementation of the Nigerian Climate Change Response Programme (NCCRP) with the following objectives: - Implement appropriate mitigation measures; - Enhance the national capacity to adapt to climate change; - Raise the profile of Climate Change Science, technology, research and development; - Increase public awareness and encourage private sector participation in combatting climate change; - Strengthen national institutions and mechanisms for effective climate change governance. Largely mitigation-focused, the technical assistance for the implementation of the NCCRP is being provided by the Conseil Santé Consortium (French consulting company) with the Department of Climate Change (DCC), Federal Ministry of Environment, as the main beneficiary. A participatory approach is adopted by the Conseil Santé Consortium involving consultations between a Technical Assistance Team (TAT), the staff of DCC and sectoral stakeholders brought together in technical Working Groups during the NCCRP inception phase workshop. Component 2 of the NCCRP is dedicated to the dissemination of climate change knowledge and raising awareness of climate change issues among diverse Nigerian audiences. Various activities are envisioned under this component, including sensitisation campaigns. A National Consultant is being recruited as a resource person and advisor to design communication and visibility materials for mass and social media. The aim of the assignment is to create compelling visual assets that will be used to increase the profile of the project and spread climate change awareness. |

| Objectives of the Mission | The goal of the consultancy is to provide technical support for the design of communication and visibility materials in support of the planned activities. |
| --- | --- |
| Specific Objectives of the Mission | The main objectives of this consultancy are outlined as follows: - Provide technical support (assistance, guidance, analytical tools, concepts, etc.) to define and maintain a streamlined visual identity for the NCCRP’s communication outputs; - Guarantee the design and layout of technical products, including guidance documents, meeting reports, policy briefs and infographics of the NCCRP; - Create a folder of high-resolution graphics/ designs/ branding to be utilised in climate change sensitisation campaigns for including posters, banners, T-Shirts, pens, face caps, etc.; - Monitor and supervise the production of campaign materials according to stipulated EU Communication and Visibility Guidelines; - Produce graphics for social media dissemination and the landing pages of the NCCRP social media accounts. (Twitter, Facebook and YouTube). |
| Estimated Schedule of Intervention of the Expert(s)’ Mission | Tasks to be Carried Out; Maximum No. of WDs. The Mission will be carried, according to the provisional Work Schedule found below.. The duration of the 70-day mission will be spread over 7 months. Note, however that during the mission, and beyond key tasks, the Consultant will be required to carry out the following: - If necessary, make propositions to the Key Experts for the improvement of the methodology suggested by Conseil Santé Consortium to achieve the objectives of the Mission; - In coordination with the Key Expert, organise meetings with the Working Group as required to perform the above tasks; - Participate in other organised workshops/meetings which might take place during the Mission; - Undertake other tasks as required to achieve the Mission´s objectives. Indicative Commencement Date: 10/2023. Sub-objective 1: Define and Mainstream the visual branding of the NCCRP and produce design templates for technical communication products of the NCCRP.. Intervention 1.1 Review the designs of currently formulated communication and visibility material and propose appropriate revisions.; 5 working days. Intervention 1.2 Design the Landing Pages of the NCCRP’s Social Media Accounts (Twitter, Facebook and YouTube).; 5 working days. Intervention 1.3 Create Design Templates for Technical Visibility Products (infographics, posters, brochures, policy briefs, investor guides and fact sheets) for routine usage.; 5 working days. Sub-objective 2: Support the Designs and Production of Graphics for the NCCRP Activities. Intervention 2.1 Produce and deliver folders of digital designs for review/suggestions/improvement at intervals as needed for implementation of the NCCRP activities upon request (Social Media Assets, T-Shirts, Pens, Fact Sheets, One-Pagers, Investor Guides, Posters, Reports, Brochures, Flyers, Banners, Face Caps, etc).; 55 Working Days. |
| Expected Outcomes and Deliverable(s) | The expected outcomes are as follows: - Result 1: The visual identity of the NCCRP is defined, modifiable and adaptable across a whole gamut of NCCRP activities; - Result 2: Graphics and designs are produced in support of Climate Change awareness activities and in compliance with EU Communication and Visibility requirements. The Mission deliverables are the following: - Deliverable 1: Compilation of feedback on NCCRP’s current design materials and a proposal on the visual identity of the NCCRP; - Deliverable 2: Design templates for technical products in a wide range of media (brochures, posters, infographics, flyers, fact sheets, reports, social media assets, etc.) that are modifiable and adaptable across a whole gamut of NCCRP activities according to the Programme’s needs; - Deliverable 3: A repository of graphics and designs upon request and as per the specifications of the TAT. |  |
| Date of Submission of Deliverable(s) | The deadline dates of the submission of deliverables to the Team Leader are as follows: - Deliverable 1: 10/2023; - Deliverable 2: 10/2023; - Deliverable 3: On demand until 05/2024. |  |
| Modalities for Submission of Deliverable(s) | - To be submitted electronically to the Team Leader and the Project Director; - Conseil Santé to submit electronically to the Project Officer at the EUD. |  |
| Structures / Actors / Stakeholders involved | - DCC - EUD - CENRAD (Centre for Environment, Renewable Natural Resources Management, Research and Development) Consulting Limited Ltd and NEST (Nigerian Environmental Study Action Team: sub-contractors of the Consortium, specialised in environment and Climate change, will support the consortium in specific tasks including the provision of local operational and technical support to the TAT, putting at the disposal of the TAT existing networks in relevant fields of the Project, etc. - Members of the two Working Groups (see the list in annex). |  |
| Title of the Position(s) | Graphic Designer |  |
| Expert(s)’ Profile(s) | - Education & Training: A University degree in Communication, HND in Business Administration and Management, Visual Arts, Graphic Design, Information Technology, or Printing Technology. A Master in Product Development Design and Management or Certificate in Climate Change Communication will be a distinct advantage. - General Experience: At least 6 years of experience of related experience as a Graphic Designer plus proficiency in Content Design, Visual Arts, Digital Imagery and Illustration. - Specific Experience: At least one previous experience managing EU visibility contracts from inception to dissemination. Proven previous experience designing social media assets. Previous experience working on environment and climate change adaptation projects is an advantage. - Technical Skills: Verified technical knowledge on the use of digital drawing and editing software (After Effects, Dreamweaver and Adobe InDesign, Photoshop, and Corel Draw) to create and share designs. Sound knowledge of media production and communication, computer operating systems, hardware, and software, logo and visual identity, motion graphics, package design, print layouts and publication, or Typography. |  |
| Global Provision for Use of Incidental Expenditure for a Mission | - If the mission will include activities outside the Duty Station, a description and breakdown of the budget is required for per diem and transport purposes. - If the activity is to be financed by the Incidental Expenditure, a detailed Excel Table is needed indicating the breakdown of the budget details. |  |