|  | Implementation of Nigeria Climate Change Response Programme (NCCRP) Contract N°: ENV/2019/409-995 |  |
| --- | --- | --- |

Terms of Reference (ToR)

SENIOR SHORT-TERM EXPERT (STE)

Provision of Technical Support for the Development of the Stakeholder Engagement and Influencing Plan and the Implementation of the Awareness-Raising Workshop to Enhance Action on Climate Change

| Reference No. of the Mission | S334/STE/2020/ToR/02-8 |  |
| --- | --- | --- |
| Date of Transmission | 01/02/2021 |  |
| Category of Expert | Senior |  |
| Key Experts Responsible | Mr Todd NGARA, Team Leader |  |
| Title of the Mission | Provision of Technical Support for the Development of the Stakeholder Engagement and Influencing Plan and the Implementation of the Awareness-Raising Workshop to Enhance Action on Climate Change |  |
| No. of Working Days (WD) | 38 Working Days |  |
| Indicative Dates | 02/2024 | 05/2024 |

| Duty Station | Abuja (FCT) |
| --- | --- |
| Mission outside of Duty Station | N/A |

| Title of the Mission |  |
| --- | --- |
| Name of Project | Implementation of Nigeria Climate Change Response Programme (NCCRP), EuropeAid/140100/DH/SER/NG |
| Contract No. | ENV/2019/409-995 |
| Reference No. of the Mission | S334/STE/2020/ToR/02-8 |
| Context and Justification | Following the ratification of the Paris Agreement in 2017, Nigeria committed itself to reduce its Greenhouse Gas (GHGs) emissions unconditionally by 20% and conditionally by 45% by 2030 in line with its Nationally Determined Contributions (NDC) pledge. To support Nigeria’s efforts towards the fulfilment of its conditional NDC target, the Federal Government of Nigeria is being supported by the European Union (EUD) through the provision of technical assistance for the implementation of the Nigerian Climate Change Response Programme (NCCRP) with the following objectives: - Implement appropriate mitigation measures; - Enhance the national capacity to adapt to climate change; - Raise the profile of Climate Change Science, technology, research and development. - Increase public awareness and encourage private sector participation in combating climate change; - Strengthen national institutions and mechanisms for effective climate change governance. Largely mitigation-focused, the technical assistance for the implementation of the NCCRP is being provided by the Conseil Santé Consortium (French consulting company) with the Department of Climate Change (DCC), Federal Ministry of Environment, as the main beneficiary. A participatory approach is adopted by the Conseil Santé Consortium involving consultations between a Technical Assistance Team (TAT), the staff of DCC and sectoral stakeholders brought together in technical Working Groups during the NCCRP inception phase workshop. Component 2 of the NCCRP is dedicated to the dissemination of climate change knowledge and raising awareness of climate change issues among diverse Nigerian audiences. One of those envisioned audiences are government and legislative stakeholders at the national and state level due to the influence such stakeholders have in enacting climate friendly policies across all sectors. Indeed, intervention 2.2 foresees the dissemination of climate change knowledge to government and legislative bodies. In order to effectively build a whole-of-government approach in the combat against Climate Change, the NCCRP envisions preparing a Stakeholder Influencing and Engagement Plan to identify pertinent climate change advocacy issues, identify key stakeholders and devise an advocacy plan accordingly. The objective is to then handover the Stakeholder Engagement and Influencing Plan for the institutional beneficiaries of the project to implement, to ensure sustainability of the programme. Additionally, the NCCRP envisages the planning of an advocacy workshop at government level to spread awareness of pertinent climate change issues in Nigeria and policy tools to address them. The workshop would be organized utilizing selected points of the Stakeholder Engagement and Influencing Plan as a foundation. The NCCRP foresees the recruitment of a Senior Climate Change Advocacy Specialist to draft the Stakeholder Engagement and Influencing Plan and to organize and conduct the Awareness Raising Workshop to Enhance Action on Climate Change. |

| Objectives of the Mission | The goal of the consultancy is to provide technical support for the planning of climate change advocacy at government and legislative levels in Nigeria and to conduct a workshop with selected stakeholders to raise awareness of pertinent climate change issues in the country. |  |
| --- | --- | --- |
| Specific Objectives of the Mission | The main objectives of this consultancy are outlined as follows: - Provide technical support for the preparation of the Stakeholder Engagement and Influencing Plan. - Provide technical support for the planning and the implementation of the Awareness Raising Workshop to Enhance Action on Climate Change. |  |
| Estimated Schedule of Intervention of the Expert(s)’ Mission | Tasks to be Carried Out; No. of WDs. The Mission will be carried, according to the provisional Work Schedule found below. The duration of the 40-day mission will be spread over 3 months, and the consultant will be expected to be based in Abuja, Nigeria for the entirety of the mission. Note however that during the mission, and beyond key tasks, the Consultant will be required to carry out the following: - If necessary, make propositions to the Key Experts for the improvement of the methodology suggested by Conseil Santé Consortium to achieve the Mission; - In coordination with the Key Expert, organise meetings with the Working Group as required to perform the above tasks; - Participate in other organised during workshops/meetings taking place during the Mission; - Undertake other tasks as required to achieve the Mission´s objectives. Indicative Commencement Date: 03/2024. Intervention A 2.2: Climate Change knowledge disseminated to different governmental bodies. Specific objective 1: Provide technical support for the implementation of the NCCRP Stakeholder Engagement and influencing Plan in collaboration with the established Working Groups. 2.2.1.1 Provide technical support for the preparation of the Stakeholder Engagement and Influencing Plan.; The objective is to define a stakeholder engagement plant and influencing plan destinated to relevant institutional stakeholders. It includes an assessment of the knowledge of those stakeholders related to climate change, the identification of key climate change-related advocacy issues, the identification of key government stakeholders and the development of an implementation plan. At the beginning of the mission, it will be defined if the implementation plan would only cover the project duration or if it would be a long-term plan to cover the period after the end of the project.. The total duration of this segment of the Mission is estimated at 20 Working Days during the first month of the assignment, which is estimated to be February 2024.. Specific Objective 2: Provide technical support for the planning and the implementation of the Awareness Raising Workshop to Enhance Action on Climate Change.. 2.2.2.1 Assist in the planning of the Awareness Raising Workshop to Enhance Action on Climate Change.; Tasks include selecting the advocacy issues that the Awareness Raising Workshop will address, identifying workshop participants, writing a concept note to present the workshop as per EU standards, work on the budgeting of the work with the admin team and preparing advocacy materials with the assistance of NKE 2.7 graphic designer.. 2.2.2.2 Facilitate and Lead the Awareness Raising Workshop to Enhance Action on Climate Change.; Based on the planning and materials prepared, the expert is expected to conduct the workshop on the selected key advocacy issues.. 2.2.2.3 Compile a Report on the Advocacy Workshop; The report should highlight feedback received on the workshop, track its impact on stakeholder climate change knowledge levels through questionnaires, bottlenecks faced in the communication of the advocacy points, and suggestions for future advocacy activities.. This portion of the mission is split into 3 parts. The first part is estimated at 10 working days, the second part at 3 working days and the second at 5 working days. The working days will be taking place over the course of 2 months (April and May 2024 tentatively).. |
| Expected Outcomes and Deliverable(s) | The expected outcomes are as follows: - Result 1: A Stakeholder Engagement and Influencing Plan is developed that identifies key climate change advocacy issues, maps key government stakeholders and details methods and advocacy tools to influence their policy decisions as well as an implementation plan - Result 2: An Awareness Raising Workshop to Enhance Action on Climate Change is organized amongst government stakeholders, leading to increased government initiatives tackling climate change. The Mission deliverables are the following: - Deliverable 1: Stakeholder Engagement and Influencing Plan identifying key climate change advocacy issues, listing key government stakeholders, and describing targeted advocacy approaches (Result 1). - Deliverable 2: Advocacy materials to be utilized in the Awareness Raising Workshop to Enhance Action on Climate Change (including presentations, videos, posters, feedback questionnaires etc) (Result 2) ; - Deliverable 3: Report on the Awareness Raising Workshop to Enhance Action on Climate Change tracking the influence the workshop had in raising knowledge levels, challenges faced in its facilitation, proposals for future advocacy events, and proposed amendments to the Stakeholder Engagement and Influencing Plan (Result 1 and 2). |
| Date of Submission of Deliverable(s) | The deadline dates of the submission of deliverables to the Team Leader are as follows: - Deliverable 1: 03/2024 - Deliverable 2: 04/2024 - Deliverable 3: 05/2024 |
| Modalities for Submission of Deliverable(s) | - To be submitted electronically to the Team Leader and the Project Director - Conseil Santé to submit electronically to the Project Officer at the EUD |
| Structures / Actors / Stakeholders involved | - DCC - EUD - Ministry of Environment - Other relevant stakeholders |
| Title of the Position(s) | One expert will be mobilised to carry out this mission: Climate Change Advocacy Expert. |
| Expert(s)’ Profile(s) | - Education & Training: Relevant bachelor’s degree in Communications, Journalism, Media Studies, Climate Change, Environmental Studies, or related. Preference will be given to candidates with master’s degrees. - General Experience: Minimum 10 years of professional experience in developing and implementing communication/ advocacy strategies in support of sustainable development-oriented projects, preferably in support of climate change adaptation and mitigation; - Specific Experience: Minimum of 2 years leading advocacy events with government stakeholder participants. - Specific Experience in using quantitative and qualitative research methods, community assessment and other tools to gather data in guiding the development of communication/ advocacy strategies and Nigeria’s legislative process; - Familiarity with Nigeria environmental/climate laws and Nigeria’s Climate Change context. |
| Global Provision for Use of Incidental Expenditure for a Mission | - If the mission will include activities outside the Duty Station, a description and breakdown of the budget is required for per diem and transport purposes. - If the activity is to be financed by the Incidental Expenditure, a detailed Excel Table is needed indicating the breakdown of the budget details. |