|  | Implementation of Nigeria Climate Change Response Programme (NCCRP) Contract N°: ENV/2019/409-995 |  |
| --- | --- | --- |

Terms of Reference (ToR)

SENIOR SHORT-TERM EXPERT (STE)

SWM Capacity Building Expert

| Reference No. of the Mission | S334/STE/2020/ToR03-9 |
| --- | --- |
| Date of Transmission | 29/11/2023 |
| Category of Expert | Senior |
| Key Expert Responsible | - Dr Todd NGARA, Team Leader - Dr Taiwo Babatunde HAMMED, Senior Key Expert on Solid Waste Management |
| Title of the Mission | Organisation of a Study Visit to France for the Technical Staff in the Public Offices |
| No. of Working Days (WD) | 28 Working Days |
| Indicative Dates | 02/2023-06/2024 |
| Duty Station | Abuja (FCT)/France |
| Mission outside of Duty Station | N/A |

| Organisation of a Study Visit to Europe for the Technical Staff in the Public Offices |  |
| --- | --- |
| Name of Project | Implementation of Nigeria Climate Change Response Programme (NCCRP), EuropeAid/140100/DH/SER/NG |
| Contract No. | ENV/2019/409-995 |
| Reference No. of the Mission | S334/STE/2020/ToR03-9 |
| Context and Justification | The overall objective of the Nigeria Climate Change Response Programme (NCCRP) is the development of a good planning framework for supporting the country in achieving the conditional 47% NDC targets, working on data quality and accuracy in order to guarantee climate action transparency, ensuring inter-sectoral institutional engagement in its implementation, as well as the definition of the waste sector to be included in the next NDCs to raise the GHG level ambition of the country. With the continuous advancement in industrialisation, particularly Small and Medium Enterprises (SMEs) in many States and the oil sector, it is envisaged that the problem of waste management will be aggravated. Training and skill acquisition in this direction is apparent as a permanent solution to combatting the problem. To achieve this, NCCRP project under Task 3 i.e., Solid Waste Management Baseline, Procedures and Communication is proposing a study tour for selected staff in the ministries and Agencies that have stake in the SWM to France. The main objective of this mission is to organise a study visit to France for technical staff in public offices at Federal and State levels to train them on advanced SWM technologies and international context of GHG emission reduction from solid waste. The visit will serve as an eye opener to country-wide solid waste management in line with global and international best practices. |
| Objectives of the Mission | The main objective of this mission is to organise advance training sessions and a study tour in Europe for public bodies (technical staff) for approximately 20 people (number to be confirmed after discussion with the beneficiaries and the donor) at Federal and State levels. The objective is to raise awareness about the linkages between climate-change, greenhouse gases emission and proper waste management. The objective is to present good practices and provide tools and knowledge for the major public stakeholders. |
| Specific Objectives of the Mission | The specific objectives of this mission are to: - Carry out pre-training need assessment among technical staff in Nigeria; - Prepare training materials in line with that training gaps identified; - Prepare a training session on advance technologies for SWM towards the relevant public staff and prepare a study tour in Europe; - Carry-out the training and accompany the study tour; - Prepare final reports of training and study tour in France. |
| Estimated Schedule of Intervention of the Expert’s Mission | The tentative schedule of intervention is shown in the Table below, following the specific objectives. N.B. It must be noted that the Expert will have a maximum of 20 Days in Europe in order to prepare the training and study tour and then to carry out the different trainings and to accompany the study tour. Task; Tasks to be Carried Out; No. of WDs. Task 1; Needs Assessment for the training and proposed area study visit in France; 7. Task 2; Preparation of training materials for facilitation of field trips and training in France, in line with that training gaps identified; 11. Task 3; Organisation of the training and study tour; 7. Task 4; Documentation and reporting on the training and EU study visit; 3. |
| Expected Outcomes and Deliverables | Detailed list of expected outcomes and corresponding deliverables are shown in the Table below: Intervention; Outcomes; Deliverables / Indicator; Comments. Task 1; The expert makes an assessment of the needs of the Federal and State Authorities in term of capacity building taking into account the scope of the project, the current knowledges of the administration and the needs expressed; Deliverable 1: Needs assessment report. The contents of the report will be submitted to SOFRECO at the beginning of the mission.; The objective of the capacity building is to raise awareness about the linkages between climate-change, greenhouse gases emission and proper waste management. The objective is to present good practices and provide tools and knowledge for the major public stakeholders. The needs assessment will take into account the scope of the project, the actual level of knowledge of the authorities, the potential training and visits in Europe. The Expert will be supported by the TAT team on-site to carry out this assessment.. Task 2; The methods of training, the content of the training & the content of the study tour are defined; Deliverable 2: - A training curriculum - PowerPoints - training manuals - Programme of the study tour - Concept Note to include area of the visit, contents of the training and methodology approach.; This preparation will be made in coordination with SOFRECO Headquarters and local team that will be in charge of the logistic. The expert will be in charge of contacting in Europe the different stakeholders to be met and the different sites to be visited. He is charge of the communication with those stakeholders and to secure the visits on site. The expert will work in collaboration with SOFRECO HQ for the logistics and the budgeting of this activity.. Task 3; Different trainings sessions and a study tour are organised in Europe. Task 4; The entire activities are documented for future references and NCCRP final report; Final report that comprises the entire activities taken place in Nigeria and France. It should include: - Training report - Study tour report - Evaluation. |
| Date of Submission of Deliverables | The table below shows the provisional schedule for the different activities. Deliverables; Provisional date of submission; Comments. Needs Assessment Report; February 2024. Preparation of the training and study tour in France; February-May 2024. Final report; By mid of June 2024. |
| Modalities for Submission of Deliverables | - To be submitted electronically to the Team Leader and the Project Director - Conseil Santé to submit electronically to the Project Officer at the EUD |
| Structures / Actors / Stakeholders involved | The structure involved in carrying out the mission are: - The Senior Key Expert on waste management who represents the TAT of Conseil Santé - Department of Climate Change (DCC) at the Ministry of Environment - Other relevant ministries, Agencies and parastatals - Identified relevant structures and actors in Europe |
| Title of the Position | SWM Capacity Building Expert |
| Expert’s Profile | Senior International Expert - Category I - Education & Training: a relevant university degree, preferably with an MSc, or equivalent, in Engineering; Environmental Health Sciences, Environmental Management, Environmental Education, Public Health or related fields. - General Experience: Minimum 15 years of in-depth technical and professional experiences in the fields of SWM and/or waste collection, waste recycling, waste to energy, proficiency in solid waste management in line with international best practices in France. - Specific Experience: - Previous experience in a waste recovery facility either government owned or private set-up with demonstrable knowledge of solid waste recycling to resources and energy including biogas and compost generation from organic waste, plastic waste recycling, solid waste characterisation and trainings on SW will be an asset; - Previous involvement in Management of projects/programmes in the field of SWM in France will be an asset; - Experience in capacity building of SWM operators; - Experience in SWM advocacy; - Previous experience in animating SWM workshop/training will be an asset. |
| Provisional Date and Duration of the Mission | The duration of the Mission is maximum 28 Working Days. The number of total working days is indicative. It can be reduced. Indicative Commencement Date: 15/02/2024 N.B.: A maximum of 15 working days can be spent in Europe. The remaining Working Days must be spent in Nigeria. All weekends and public holidays are not considered to be Working Days unless previous exceptional approval has been obtained from the FMoE and the EUD. |
| Global Provision for Use of Incidental Expenditure for a Mission | In the event that the mission will include activities outside of the Duty Station, a description and breakdown of the budget is required for per diem, transport. If the activity is to be financed by the Incidental Expenditure, a detailed Excel Table is needed indicating the breakdown of the budget details. |
| Dates of Approval from the FMoE and the EUD |  |

ANNEXES:

# Included as Annexes to this mission are:

- Concept Note

- Organisation and methodology of the Conseil Santé Consortium for the NCCRP implementation

- ToR for the NCCRP